## current working copy
| Last updated: | 2024-11-21
Transportation Coaliton Plan
Section IV. - 5-Year Plan
| Project Name | Description | Estimated Cost (2024 Dollars) | Recommended Funding Source | Current Year (FY 25) |  | Year #1 (FY 26) |  | Year #2 (FY 27 |  |  | Year #3 (FY 28) |  | Year #4 (FY 29) |  | Year #5 (FY 30) |  | Notes
[7 empty] | July 1, 25 - June 30, 26 |  | July 1, 26 - June 30, 27 |  |  | July 1, 27 - June 30, 28 |  | July 1, 28 - June 30, 29 |  | July 1, 29 - June 30, 30
[5 empty] | Planning | Construction | Planning | Construction | Planning | Construction | Construction | Planning | Construction | Planning | Construction | Planning | Construction
1 | Lincoln Road/Old Town Hall Crosswalk and Table | Design and construction of crosswalk and table |  | Chapter 90 | [13 empty] | In process. Expect to construct in fall 2025
2 | Repaving Tower Road | Annual repaving project/s. |  | Chapter 90 | [13 empty] | Repaving Completed.
3 | Route 2/Bedford Road Crosswalk Improvements | Start by sending letter to Commonwealth (MHD). Ask them to undertake project. | no up-front costs; hope would be that MHD would implement | N/A | TBD | [12 empty] | Goal would be to convince MHD to undertake the project.
4 | Route 117/Old Sudbury Road Crosswalk | new crosswalk across 117 cutting through existing pedestrian island | 250000 | Complete Streets #3 priority; Complete Streets Funding | [13 empty] | Currently appears as Complete Streets #3 priority; Contract awarded July 2025 to be completed by 12/31/2025.
5 | Lincoln Road/Ballfield Road Slip Lane & Ballfield Road Design Improvements | Start by running a consultant-managed pilot of slip lane closure with barrels or other barriers. Concurrently, design Ballfield Road circulation improvements. | Minimal test-stage costs $50,000 or less; need construction estimate for reconfiguring the new intersection | DPW Budget Study; TBD for construction; likely to require cash capital or other town funds, grant possible | [13 empty] | If test is successful, would want to make sure the project is sequenced properly with the repaving of the Ballfield Road loop after Community Center completed in 2026. Need John to provide estimate of cost of construction
6 | Route 117/Tower Road Crosswalk and Possible Island | Pedestrian and Bicycle Safety Improvements | $250,000 or more | Complete Streets assumed to be primary source, or town funds | [13 empty] | Contingent upon easement. HIS has provided 2 concepts. Cost likely to be above $250,000. Currently #6 for Complete Streets. Application in fall of 2027
7 | Village Center Pedestrian Plan | Study pedstrian infrastructure in Village Center when RLF presents a plan | 100000 | [5 empty] | TBD |  |  |  | TBD |  |  |  |  | Very rough estimate of $100,000 to develop comprehensive plan for improving pedestrian circulation in Village Center
8 | Route 126/Farrar Road Crosswalk | Crosswalk south of Farrar Road | $50,000 or less | Chapter 90 | [13 empty] | IMEG has provided a concept plan. Cost is relativley modest. Site lines good.
9 | Trapelo Road/Lexington Road Crosswalk | new painted crosswalk with sign package; no beacons; no raised table | $50,000 or less | Chapter 90; | [13 empty] | Could also consider bundling the three crosswalk "painting" projects and asking for Capcom funds
10 | Trapelo Road/Page Road Crosswalk | new painted crosswalk with sign package; no beacons; no raised table | $50,000 or less | Chapter 90; | [13 empty] | Could also consider bundling the three crosswalk "painting" projects and asking for Capcom funds
11 | Weston Road | Scope TBD. Improve pedestrian and bicycle safety. | 500000 + depending on scope | Borrowing | [13 empty] | Complex project. Funds for study included in Year 5. TBD whether there is a viable project
12 | Route 117 Mt. Misery | Path extension on south side of 117 and crosswalk relocation to vicinity of parking lot | $250,000 or more | Cash Capital; | [13 empty] | Need to investigate why the path was terminated at current location. Likely to require easements. NOT CURRENTLY INCLUDED IN COMPLETE STREETS PLAN. Doesn't appear to be a viable project
OTHER PROJECTS TO CONSIDER, ADDED AFTER JUNE 2024, FOR CONSIDERATION IN PRIORITIZATION DISCUSSIONS SUMMER 2025
| Project Name | Description | Proponents | Date Added
| Tower Road traffic calming after repaving, between Lincoln Rd and Beaver Pond |  | Peter Von Mertens | 2024-11-21

## Jun2024 approved version, more
| Last updated: | 2024-11-21
Transportation Coaliton Plan
Section IV. - 5-Year Plan
| Project Name | Description | Project # (Among 9 Projects) | Estimated Cost (2024 Dollars) | Recommended Funding Source | Current Year (FY 25) |  | Year #1 (FY 26) |  | Year #2 (FY 27 |  |  | Year #3 (FY 28) |  | Year #4 (FY 29) |  | Year #5 (FY 30) |  | Notes
[8 empty] | July 1, 25 - June 30, 26 |  | July 1, 26 - June 30, 27 |  |  | July 1, 27 - June 30, 28 |  | July 1, 28 - June 30, 29 |  | July 1, 29 - June 30, 30
[6 empty] | Planning | Construction | Planning | Construction | Planning | Construction | Construction | Planning | Construction | Planning | Construction | Planning | Construction
1 | Lincoln Road/Old Town Hall Crosswalk and Table | Design and construction of crosswalk and table | Not Listed |  | Chapter 90 | [13 empty] | In process. Expect to construct in 2024
2 | Repaving Tower Road and ________ | Annual repaving project/s. | Not Listed |  | Chapter 90 | [13 empty] | Contract expected to be awarded this summer.
3 | Route 2/Bedford Road Crosswalk Improvements | Start by sending letter to Commonwealth (MHD). Ask them to undertake project. | #2 | no up-front costs; hope would be that MHD would implement | N/A | [13 empty] | Goal would be to convince MHD to undertake the project. Town has excellent relations with MHD Regional Office.
5 | Old Sudbury Road Crosswalk | new crosswalk across 117 cutting through existing pedestrian island | #9 | 250000 | Complete Streets #3 priority; Safe Routes to School possibility | [13 empty] | Currently appears as Complete Streets #3 priority; Could apply for Saft Rtes to School if have ubilt up enough points. Application due Oct 2024 construct spring 2025
4 | Lincoln Road/Ballfield Road Slip Lane & Repaving | Start by running a consultant-managed pilot of slip lane closure with barrels or other barriers. Concurrently, design Ballfield Road repaving including improved intersection and improved ped/bike facilities. | #4 | Minimal test-stage costs $50,000 or less; need construction estimate for reconfiguring the new intersection | DPW Budget Study; TBD for construction; likely to require cash capital or other town funds or Safe Routes to School | [13 empty] | If test is successful, would want to make sure the project is sequenced properly with the repaving of the Ballfield Road loop after Community Center completed in 2026. Need John to provide estimate of cost of construction
9 | Route 117/Tower Road Crosswalk and Island | Construct crosswalk including pedestrian island. | #1 | $250,000 or more | Complete Streets assumed to be primary source, or town funds | [13 empty] | Contingent upon easement. HIS has provided 2 concepts. Cost likely to be above $250,000. Currently #6 for Complete Streets. Application in fall of 2027
12 | Village Center Pedestrian Plan | Study pedstrian infrastructure in Village Center when RLF presents a plan | N/A | 100000 | Chapter 90 or Cash Capital | [13 empty] | Very rough estimate of $100,000 to develop comprehensive plan for improving pedestrian facilities in Village Center
6 | Route 126/Farrar Road Crosswalk | Crosswalk south of Farrar Road | #3 | $50,000 or less | Chapter 90 | [13 empty] | HSI has provided a concept plan. Cost is relativley modest. Site lines good.
7 | Trapelo Road/Lexington Road Crosswalk | new painted crosswalk with sign package; no beacons; no raised table | #7 | $50,000 or less | Chapter 90; | [13 empty] | Could also consider bundling the three crosswalk "painting" projects and asking for Capcom funds
8 | Trapelo Road/Page Road Crosswalk | new painted crosswalk with sign package; no beacons; no raised table | #8 | $50,000 or less | Chapter 90; | [13 empty] | Could also consider bundling the three crosswalk "painting" projects and asking for Capcom funds
11 | Weston Road | Scope TBD; perhaps new path segment; some discusison of one-way | #5 | 500000 | Borrowing | [13 empty] | Complex project. Funds for study included in Year 5. TBD whether there is a viable project
10 | Route 117 Mt. Misery | Path extension on south side of 117 and crosswalk relocation to vicinity of parking lot | #6 | $250,000 or more | Cash Capital; | [13 empty] | Need to investigate why the path was terminated at current location. Likely to require easements. NOT CURRENTL INCLUDED IN COMPLETE STREETS PLAN. Doesn't appear to be a viable project

## Jun2024 approved by Trans Coal
| Last updated: | 2024-11-21
Transportation Coaliton Plan
Section IV. - 5-Year Plan
| Project Name | Description | Project # (Among 9 Projects) | Estimated Cost (2024 Dollars) | Recommended Funding Source | Current Year (FY 25) |  | Year #1 (FY 26) |  | Year #2 (FY 27 |  |  | Year #3 (FY 28) |  | Year #4 (FY 29) |  | Year #5 (FY 30) |  | Notes
[8 empty] | July 1, 25 - June 30, 26 |  | July 1, 26 - June 30, 27 |  |  | July 1, 27 - June 30, 28 |  | July 1, 28 - June 30, 29 |  | July 1, 29 - June 30, 30
[6 empty] | Planning | Construction | Planning | Construction | Planning | Construction | Construction | Planning | Construction | Planning | Construction | Planning | Construction
1 | Lincoln Road/Old Town Hall Crosswalk and Table | Design and construction of crosswalk and table | Not Listed |  | Chapter 90 | [13 empty] | In process. Expect to construct in 2024
2 | Repaving Tower Road and ________ | Annual repaving project/s. | Not Listed |  | Chapter 90 | [13 empty] | Contract expected to be awarded this summer.
3 | Route 2/Bedford Road Crosswalk Improvements | Start by sending letter to Commonwealth (MHD). Ask them to undertake project. | #2 | no up-front costs; hope would be that MHD would implement | N/A | [13 empty] | Goal would be to convince MHD to undertake the project. Town has excellent relations with MHD Regional Office.
4 | Lincoln Road/Ballfield Road Slip Lane & Repaving | Start by running a consultant-managed pilot of slip lane closure with barrels or other barriers. Concurrently, design Ballfield Road repaving including improved intersection and improved ped/bike facilities. | #4 | Minimal test-stage costs $50,000 or less; need construction estimate for reconfiguring the new intersection | DPW Budget Study; TBD for construction; likely to require cash capital or other town funds or Safe Routes to School | [13 empty] | If test is successful, would want to make sure the project is sequenced properly with the repaving of the Ballfield Road loop after Community Center completed in 2026. Need John to provide estimate of cost of construction
5 | Old Sudbury Road Crosswalk | new crosswalk across 117 cutting through existing pedestrian island | #9 | 250000 | Complete Streets #3 priority; Safe Routes to School possibility | [13 empty] | Currently appears as Complete Streets #3 priority; Could apply for Saft Rtes to School if have ubilt up enough points. Application due Oct 2024 construct spring 2025
6 | Route 126/Farrar Road Crosswalk | Crosswalk south of Farrar Road | #3 | $50,000 or less | Chapter 90 | [13 empty] | HSI has provided a concept plan. Cost is relativley modest. Site lines good.
7 | Trapelo Road/Lexington Road Crosswalk | new painted crosswalk with sign package; no beacons; no raised table | #7 | $50,000 or less | Chapter 90; | [13 empty] | Could also consider bundling the three crosswalk "painting" projects and asking for Capcom funds
8 | Trapelo Road/Page Road Crosswalk | new painted crosswalk with sign package; no beacons; no raised table | #8 | $50,000 or less | Chapter 90; | [13 empty] | Could also consider bundling the three crosswalk "painting" projects and asking for Capcom funds
9 | Route 117/Tower Road Crosswalk and Island | Construct crosswalk including pedestrian island. | #1 | $250,000 or more | Complete Streets assumed to be primary source, or town funds | [13 empty] | Contingent upon easement. HIS has provided 2 concepts. Cost likely to be above $250,000. Currently #6 for Complete Streets. Application in fall of 2027
10 | Route 117 Mt. Misery | Path extension on south side of 117 and crosswalk relocation to vicinity of parking lot | #6 | $250,000 or more | Cash Capital; | [13 empty] | Need to investigate why the path was terminated at current location. Likely to require easements. NOT CURRENTL INCLUDED IN COMPLETE STREETS PLAN. Doesn't appear to be a viable project
11 | Weston Road | Scope TBD; perhaps new path segment; some discusison of one-way | #5 | 500000 | Borrowing | [13 empty] | Complex project. Funds for study included in Year 5. TBD whether there is a viable project
12 | Village Center Pedestrian Plan | Study pedstrian infrastructure in Village Center when RLF presents a plan | N/A | 100000 | Chapter 90 or Cash Capital | [13 empty] | Very rough estimate of $100,000 to develop comprehensive plan for improving pedestrian facilities in Village Center